## 2022
Progress Report Client and Loading
Konsultan |  | : TRI AMDANI KUMBASARI
Tgl Update |  | : 21 Juli 2021
A. Progress Client
No | Client |  | Project |  | Progress |  |  | Mandays |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | Des 21 |  | Total Actual | Remark | Action Plan | Status | Need Help
[5 empty] | Plan | Aktual | Aktual Progres | Kontrak | Terpakai | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | PT. Wangsari Multi Utama |  | ISO 14001:2015 |  | 100% | 0% | 0% | 20 | 0 | [26 empty] | 0
2 | PT. Kirana Jaya Multi |  | ISO 14001:2015 |  | 100% | 25% | 25% | 20 | 5 |  |  |  |  | 4 | 3 | 1 | 1 | [17 empty] | 1 | 5 | 1 MD untuk Audit Konsultan (Bp Holan)
3 | PT. Adharco |  | ISO 14001:2015 |  | 100% | 0% | 0% | 20 | 0 | [26 empty] | 0
4 | PT. Djabesmen |  | ISO 14001:2015 |  | 100% | 97.83% | 97.83% | 23 | 22.5 | 4 | 2 | 4 | 1.5 | 4 | 1 | 5 | 5 | 2 | 1 |  |  | 1 | [12 empty] | 12 | 22.5 | 10 MD terpakai di tahun 2021 + 2 MD untuk Audit Konsultan (Bp Cahyadi & Mas Dhywa)
5 | PT. Marugo Rubber Indonesia |  | ISO 14001:2015 |  | 100% | 76% | 76% | 25 | 19 | 4 | 3 | 4 | 4 | 4 | 1 | 2 | 1 |  |  | 2 | [14 empty] | 10 | 19 | 8 MD terpakai di tahun 2021 + 2 MD untuk Audit Konsultan (Bp Lis & Mas Dhywa)
6 | PT. Trinseo Materials Indonesia |  | ISO 14001:2015 |  | 100% | 96% | 96% | 25 | 24 | 4 | 3 | 4 | 4 | 4 | 4 | 2 | 1 | 3 | 1 |  |  | 1 | [12 empty] | 11 | 24 | 8 MD terpakai di tahun 2021 + Audit Konsultan 2 MD (Pak Bani & Mas Dhywa) + 1 MD (Konsultasi dgn Pak Bani)
7 | PT. Toyoda Gosei Indonesia |  | ISO 45001:2018 |  | 100% | 20% | 20% | 25 | 5 | [8 empty] | 3 | 3 | 5 | 2 | 5 | [13 empty] | 5
8 | PT. Asahi Seiren Indonesia |  | ISO 45001:2018 |  | 100% | 71.43% | 71.43% | 7 | 5 | [6 empty] | 5 | 5 | [18 empty] | 5 | 1 MD untuk Mas dhywa
[5 empty] | T O T A L |  | MD All Client |  |  | 12 | 8 | 12 | 9.5 | 16 | 9 | 15 | 13 | 8 | 5 | 7 | 2 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
MD Konsultan Other
[7 empty] | MD Konsultan Owner |  |  | 12 | 8 | 12 | 9.5 | 16 | 9 | 15 | 13 | 8 | 5 | 7 | 2 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
B. Chargable : Team Project / IHT / Audit Konsultan
No | Client |  | Activity |  | Progress |  |  | All Mandays |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | Des 21 |  | Total Plan | Remark |  |  | Need Help
[8 empty] | Plan | Actual | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | PT Aica Indira --> Lem Fox |  | IHT ISO 45001 |  | 100% |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [20 empty] | 1
2 | PT. Furukawa |  | Audit ISO 14001:2015 |  | 100% |  |  | 1 | 1 | [6 empty] | 1 | 1 | [18 empty] | 1
3 | PT. Yachio |  | Audit ISO 14001 & 45001 |  | 100% |  |  | 1 | 1 | [8 empty] | 1 | 1 | [16 empty] | 1
4 | PT. Yachio |  | Perbaikan Audit |  | 100% |  |  | 1 | 1 | [10 empty] | 1 | 1 | [14 empty] | 1
5 |  |  |  |  | #DIV/0! |  |  | 0 | 0 | [26 empty] | 0
[7 empty] | TOTAL |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Non Chargable : Buat Report di Kantor, Ikut Persentasi Sales, Meeting di Kantor, Program Kerja Perusahaan, Ikut Training
No | Activity |  |  | Client |  |  |  | All Mandays |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | Des 21 |  | Total Plan | Remark |  |  | Need Help
[8 empty] | Plan | Actual | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | WFH : Dokumen Client |  |  | PT. Djabesmen |  |  |  | 1 | 5 |  | 1 | 1 | 2 |  | 2 | [20 empty] | 1 | Sentral covid
2 | WFH : Dokumen Client |  |  | PT. Marugo |  |  |  | 0 | 7 |  | 2 |  | 1 |  | 2 |  |  |  | 2 | [16 empty] | 0 | - Persiapan Audit BS - Dokumen Control Sentral
3 | WFH : Dokumen Client |  |  | PT. Trinseo |  |  |  | 1 | 1 |  |  | 1 | 1 | [22 empty] | 1
4 | WFH : Dokumen Client |  |  | PT. KJM |  |  |  | 0 | 1 | [5 empty] | 1 | [20 empty] | 0
5 | Kantor | [6 empty] | 18 | 22 | 6 | 6 | 3 | 3 | 3 | 5 | 2 | 2 | 3 | 5 | 1 | 1 | [14 empty] | 18
6 | WFH : Dokumen Sentral | [6 empty] | 2 | 6.5 |  |  |  | 1.5 |  | 1 |  | 2 | 2 | 2 | [16 empty] | 2
7 | WFH : Dokumen Client |  |  | PT. Toyoda Gosei Indonesia |  |  |  | 0 | 1 | [7 empty] | 1 | [18 empty] | 0
8 | [7 empty] | 0 | 0 | [26 empty] | 0
[8 empty] | TOTAL |  | 6 | 9 | 5 | 8.5 | 3 | 11 | 2 | 5 | 5 | 9 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. GRAFIK LOADING dan PERFORMANCE KONSULTAN :
|  |  |  | BULAN | [5 empty] | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | Des 21 | [6 empty] | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
| Jan | Maret | Mei | Mandays Planning | [5 empty] | 18 |  | 17 |  | 20 |  | 18 |  | 14 |  | 9 |  | 7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Cuti | 1 | 1 | 1 | Mandays Standard (Hari Kerja Sebulan) | [5 empty] | 21 |  | 18 |  | 22 |  | 19 |  | 15 |  | 21 |  | 21 |  | 18 |  | 22 |  | 19 |  | 21 |  | 22 |  | 21
Sakit | 3 |  |  | % Plan vs Standard | [5 empty] | 85.71% |  | 94.44% |  | 90.91% |  | 94.74% |  | 93.33% |  | 42.86% |  | 33.33% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | [6 empty] | 21 | 23 | 21 | 21
Masuk Sabtu |  |  | 1 | Mandyas Actual | [5 empty] | 17 |  | 18 |  | 21 |  | 19 |  | 15 |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 34
|  |  |  | % Actual vs Plan | [5 empty] | 80.95% |  | 105.9% |  | 105% |  | 105.6% |  | 107.1% |  | 44.44% |  | 0% |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
|  |  |  | Chargable Mandays | [5 empty] | 8 |  | 9.5 |  | 10 |  | 14 |  | 6 |  | 3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 34
|  |  |  | % Chargable vs Standard | [5 empty] | 38.1% |  | 52.78% |  | 45.45% |  | 73.68% |  | 40% |  | 14.29% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 161.9%
|  |  |  | Target % Chargable vs Standard | [5 empty] | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85%
Konsultan
Tri Amdani Kumbasari

## 2021
Progress Report Client and Loading
Konsultan |  | : TRI AMDANI KUMBASARI
Tgl Update |  | : 21 Juli 2021
A. Progress Client
No | Client |  | Project |  | Progress |  |  | Mandays |  | 2021-01-01 |  | 2021-02-01 |  | 2021-03-01 |  | 2021-04-01 |  | 2021-05-01 |  | 2021-06-01 |  | 2021-07-01 |  | 2021-08-01 |  | 2021-09-01 |  | 2021-10-01 |  | 2021-11-01 |  | 2021-12-01 |  | 2022-01-01 |  | Total Actual | Remark | Action Plan | Status | Need Help
[5 empty] | Plan | Aktual | Aktual Progres | Kontrak | Terpakai | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | PT. Wangsari Multi Utama |  | ISO 14001:2015 |  | 100% | 20% | 20% | 20 | 4 |  |  | 1 | 1 | 1 | 1 | 2 | 2 | [18 empty] | 4 | Tertunda karena Covid dan masalah internal (produksi), sudah dikontak setiap bulan, terakhir respon di bulan Juli, setelah itu di WA tidak pernah respon Melanjutkan Project dari Ibu Galih, total MD terpakai 5 MD Des : 1, Jan : 3, Feb : 1 (Total MD : 19)
2 | PT. Kirana Jaya Multi |  | ISO 14001:2015 |  | 100% | 60% | 60% | 20 | 12 | 1 | 1 | 3 | 3 | 5 | 3 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | [6 empty] | 1 | 1 | 1 | 1 |  |  | 12 | Info dari Bu Romi tertunda karena masalah produksi internal, rencana minggu depan diinfokan kembali | Follup minggu depan, remind
3 | PT. Adharco |  | ISO 14001:2015 |  | 100% | 40% | 40% | 20 | 8 | [26 empty] | 8 | Planning buat plan baru jadi ISO tertunda, rencana ISO diterapkan di plan baru, info pertengahan Tahun 2021
4 | PT. Djabesmen |  | ISO 14001:2015 |  | 100% | 43.48% | 43.48% | 23 | 10 | [16 empty] | 3 | 2 | 3 | 2 | 3 | 3 | 3 | 3 |  |  | 10
5 | PT. Marugo Rubber Indonesia |  | ISO 14001:2015 |  | 100% | 32% | 32% | 25 | 8 | [18 empty] | 1 | 1 | 6 | 6 | 1 | 1 |  |  | 8
6 | PT. Asahi Seiren Indonesia |  | ISO 45001:2018 |  | 100% | 32% | 32% | 25 | 8 | [16 empty] | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 1 |  |  | 8
7 | PT. Trinseo Materials Indonesia |  | ISO 14001:2015 |  | 100% | 32% | 32% | 25 | 8 | [16 empty] | 3 | 3 | 4 | 2 | 4 | 3 |  |  |  |  | 8
[5 empty] | T O T A L |  | MD All Client |  |  | 1 | 1 | 4 | 4 | 6 | 4 | 3 | 3 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 8 | 7 | 10 | 7 | 17 | 16 | 6 | 6 | 0 | 0
[7 empty] | MD Konsultan Other | [6 empty] | 1 | 1 | [6 empty] | 1 | 1 | 2 | 2
[7 empty] | MD Konsultan Owner |  |  | 1 | 1 | 4 | 4 | 5 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | -2 | -2 | 8 | 7 | 10 | 7 | 17 | 16 | 6 | 6 | 0 | 0
B. Chargable : Team Project / IHT / Audit Konsultan
No | Client |  | Activity |  | Progress |  |  | All Mandays |  | 2021-01-01 |  | 2021-02-01 |  | 2021-03-01 |  | 2021-04-01 |  | 2021-05-01 |  | 2021-06-01 |  | 2021-07-01 |  | 2021-08-01 |  | 2021-09-01 |  | 2021-10-01 |  | 2021-11-01 |  | 2021-12-01 |  | 2022-01-01 |  | Total Plan | Remark |  |  | Need Help
[8 empty] | Plan | Actual | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | PT. Fujiko Indonesia |  | Konsultasi ISO 14001:2015 |  | 60% |  |  | 5 | 3 | 4 | 3 |  |  | 1 | [21 empty] | 5
2 | PT. Camelia Metal |  | Audit Konsultan |  | 100% |  |  | 3 | 3 | 1 | 1 | 2 | 2 | [22 empty] | 3
3 | PT. Shuangying International |  | Konsultasi ISO 14001:2015 |  | 100% |  |  | 1 | 1 | 1 | 1 | [24 empty] | 1
4 | PT. Inter Aneka Lestari Kimia |  | Audit Konsultan |  | 100% |  |  | 1 | 1 |  |  | 1 | 1 | [22 empty] | 1
5 | PT. Gaya Motor |  | Audit Konsultan |  | 100% |  |  | 2 | 2 |  |  |  |  | 2 | 2 | [20 empty] | 2
6 | PT. Stanley |  | Audit Konsultan |  | 100% |  |  | 1 | 1 |  |  |  |  | 1 | 1 | [20 empty] | 1
7 | PT. Selalu Cinta Indonesia |  | Konsultasi ISO 14001 & ISO 45001 |  | 100% |  |  | 13 | 13 | [6 empty] | 7 | 7 | [6 empty] | 6 | 6 | [10 empty] | 13
8 | PT. YPMI |  | Konsultasi ISO 45001:2018 Audit Konsultan |  | 100% |  |  | 2 | 2 | [16 empty] | 1 | 1 | 1 | 1 | [6 empty] | 2
9 | PT. Technoplast |  | Audit Konsultan |  | 100% |  |  | 1 | 1 | [10 empty] | 1 | 1
10 | PT. WKR |  | Audit Konsultan |  | #DIV/0! |  |  | 0 | 0
11 | PT. Ftech |  | Audit Konsultan |  | 100% |  |  | 1 | 1 | [10 empty] | 1 | 1
12 | Mahasiswa |  | Training Awarness ISO 45001:2018 |  | 100% |  |  | 1 | 1 | [12 empty] | 1 | 1
13 | Webinar |  | Program Kedaruratan |  | 100% |  |  | 1 | 1 | [14 empty] | 1 | 1
14 | PT. Cikarang Listrindo |  | Audit Konsultan |  | 100% |  |  | 2 | 2 | [16 empty] | 1 | 1 | 1 | 1
15 | PT. ITSP |  | Audit Konsultan |  | 100% |  |  | 1 | 1 | [14 empty] | 1 | 1
16 | PT. PLTU Tanjung Jati B |  | DPBB |  | 100% |  |  | 3 | 3 | [16 empty] | 3 | 3
17 | PT. Yachio |  | Kick Off ISO 45001:2015 |  | 100% |  |  | 2 | 2 | [10 empty] | 1 | 1 | [6 empty] | 1 | 1 | [6 empty] | 2
18 | PT. MII |  | Konsultasi |  | 100% |  |  | 1 | 1 | [18 empty] | 1 | 1
19 | PT. Furukawa |  | Konsultasi ISO 14001:2015 |  | 100% |  |  | 1 | 1 | [20 empty] | 1 | 1
20 | PT. Cogindo |  | SMK3 |  | 100% |  |  | 11 | 11 | [22 empty] | 11 | 11
21 | PT. KAI |  | Konsultan ISO14001:2015 |  | 100% |  |  | 4 | 4 | [6 empty] | 2 | 2 | 2 | 2 | [16 empty] | 4
[7 empty] | TOTAL |  |  | 6 | 5 | 3 | 3 | 4 | 3 | 9 | 9 | 2 | 2 | 3 | 3 | 1 | 1 | 8 | 8 | 5 | 5 | 4 | 4 | 1 | 1 | 11 | 11 | 0 | 0
C. Non Chargable : Buat Report di Kantor, Ikut Persentasi Sales, Meeting di Kantor, Program Kerja Perusahaan, Ikut Training
No | Activity |  |  | Client |  |  |  | All Mandays |  | 2021-01-01 |  | 2021-02-01 |  | 2021-03-01 |  | 2021-04-01 |  | 2021-05-01 |  | 2021-06-01 |  | 2021-07-01 |  | 2021-08-01 |  | 2021-09-01 |  | 2021-10-01 |  | 2021-11-01 |  | 2021-12-01 |  | 2022-01-01 |  | Total Plan | Remark |  |  | Need Help
[8 empty] | Plan | Actual | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | WFH : Dokumen SSC, Dokumen Client, Action Plan | [6 empty] | 26 | 69 |  | 8 | 5 | 11 | 2 | 4 | 2 | 3 |  | 1 | 3 | 7 | 2 | 7 | 4 | 8 | 3 | 6 | 1 | 4 | 1 | 4 | 3 | 6 |  |  | 26 | Sentral covid
2 | Office | [6 empty] | 32 | 52 | 2 | 4 |  | 2 | 6 | 8 | 2 | 5 | 6 | 11 | 3 | 7 | 10 | 10 | 2 | 2 | 1 | 1 |  | 2 | [6 empty] | 32 | - Persiapan Audit BS - Dokumen Control Sentral
3 | Training SIMPEL / Seminar Dokumen Lingkungan | [6 empty] | 2 | 2 | 1 | 1 |  |  |  |  | 1 | 1 | [18 empty] | 2
4 | Kemnaker : Dokumen PJK3 | [6 empty] | 2 | 2 | 1 | 1 |  |  | 1 | 1 | [20 empty] | 2
5 | Meeting | [6 empty] | 1 | 1 |  |  | 1 | 1 | [22 empty] | 1
6 | Audit SSC | [6 empty] | 1 | 1 | [8 empty] | 1 | 1 | [16 empty] | 1
7 | Perbaikan Dokumen ISO 14001:2015 |  |  | PT. KAI |  |  |  | 0 | 0 | [26 empty] | 0
8 | Webinar | [6 empty] | 3 | 3 | [8 empty] | 1 | 1 | 1 | 1 |  |  | 1 | 1 | [10 empty] | 3
9 | Training Awarnes dan Internal Audit ISO 14001:2015 |  |  |  | PT. KAI | [14 empty] | 2 | 2
10 | Training IADL |  |  | PT. Semen Gresik | [15 empty] | 1 | 1
11 | Disnaker Semarang |  |  | PLTU Tanjung Jati B | [21 empty] | 1 | 1
12 | Training Risk Manajemen |  |  | PT. Senopati |  |  |  | 1 | 1 | [10 empty] | 1 | 1 | [14 empty] | 1
[8 empty] | TOTAL |  | 4 | 14 | 6 | 14 | 9 | 13 | 5 | 9 | 8 | 14 | 11 | 19 | 12 | 17 | 7 | 11 | 5 | 8 | 1 | 6 | 1 | 4 | 3 | 6 | 0 | 0
D. GRAFIK LOADING dan PERFORMANCE KONSULTAN :
|  |  |  | BULAN | [5 empty] | 2021-01-01 |  | 2021-02-01 |  | 2021-03-01 |  | 2021-04-01 |  | 2021-05-01 |  | 2021-06-01 |  | 2021-07-01 |  | 2021-08-01 |  | 2021-09-01 |  | 2021-10-01 |  | 2021-11-01 |  | 2021-12-01 |  | 2022-01-01 | [6 empty] | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
| Note: 16 Juli Cuti |  |  | Mandays Planning | [5 empty] | 11 |  | 13 |  | 18 |  | 17 |  | 11 |  | 14 |  | 13 |  | 13 |  | 18 |  | 15 |  | 19 |  | 20 |  | 0
| 16 Agt Cuti |  |  | Mandays Standard (Hari Kerja Sebulan) | [5 empty] | 21 |  | 21 |  | 21 |  | 21 |  | 17 |  | 21 |  | 20 |  | 20 |  | 22 |  | 20 |  | 22 |  | 23 |  | 21
| 6 Sept Cuti |  |  | % Plan vs Standard | [5 empty] | 52.38% |  | 61.9% |  | 85.71% |  | 80.95% |  | 64.71% |  | 66.67% |  | 65% |  | 65% |  | 81.82% |  | 75% |  | 86.36% |  | 86.96% |  | 0% | [6 empty] | 21 | 23 | 21 | 21
| 6-7 Des Cuti |  |  | Mandyas Actual | [5 empty] | 20 |  | 21 |  | 19 |  | 21 |  | 17 |  | 22 |  | 18 |  | 17 |  | 20 |  | 17 |  | 21 |  | 23 |  | 0
| 29-29 Masuk |  |  | % Actual vs Plan | [5 empty] | 95.24% |  | 161.5% |  | 105.6% |  | 123.5% |  | 154.5% |  | 157.1% |  | 138.5% |  | 130.8% |  | 111.1% |  | 113.3% |  | 110.5% |  | 115% |  | #DIV/0!
|  |  |  | Chargable Mandays | [5 empty] | 6 |  | 7 |  | 6 |  | 12 |  | 3 |  | 3 |  | 1 |  | 6 |  | 12 |  | 11 |  | 17 |  | 17 |  | 0
|  |  |  | % Chargable vs Standard | [5 empty] | 28.57% |  | 33.33% |  | 28.57% |  | 57.14% |  | 17.65% |  | 14.29% |  | 5% |  | 30% |  | 54.55% |  | 55% |  | 77.27% |  | 73.91% |  | 0%
|  |  |  | Target % Chargable vs Standard | [5 empty] | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85%
Konsultan
Tri Amdani Kumbasari