## FORMAT AGT 22
Progress Report Client and Loading
Konsultan |  | : Lisdiyanto
Tgl Update |  | : 31 AGUSTUS 2022
A. Progress Client
No | Client |  | Project |  | Progress |  | Mandays |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | Remark | Action Plan
[5 empty] | Plan | Aktual | Kontrak | Terpakai | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | LG Innotek |  | Konsultasi ISO 50001 |  | 100% | 0% | [18 empty] | 5 | 4 | 5 |  | 5 |  | 5 |  | Audit stage 1 W4 November 2022
2 | Summit Seoyon |  | Integrasi IATF & 14001 |  | 100% | 0% | [18 empty] | 3 | 1 | 4 |  | 2 |  | 2 |  | Audit stage 1 W4 Desember 2022
3 | Hitachi Metals Indonesia |  | Inspection besr-basis iso 17022 |  | 100% | 0% | [18 empty] | 3 | 2 | 3 |  | 3 |  | 3 |  | End of Contract - Desember 2022
4 | PT Cataler Indonesia |  | BCMS - ISO 22301 |  | 100% | 100% | [26 empty] | Sudah Lulus - Finished
5 | PLP - Cikarang Indonesia |  | Inspection besr-basis iso 17022 |  | 100% | 100% | [26 empty] | Sudah Lulus - Finished
6 | PT SMU - Wings Grup |  | ISO 9001 |  | 100% | 100% | [26 empty] | Sudah Lulus - Finished
7 | Techno Plast |  | ISO 13845 & CE Marking |  | 100% | 100% | [26 empty] | Sudah Lulus - Finished
4
[5 empty] | T O T A L | MD All Client |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 7 | 12 | 0 | 10 | 0 | 10 | 0
MD Konsultan Other
| ` |  |  |  |  | MD Konsultan Owner |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 7 | 12 | 0 | 10 | 0 | 10 | 0
B. Chargable : Team Project / IHT / Audit Konsultan
No | Client |  | Activity |  | Progress |  | All Mandays |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | Remark | Need Help
[7 empty] | Plan | Actual | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | Tuffindo |  | Warehouse Management |  |  |  | 2 | 1 | [16 empty] | 2 | 1
2 | IBARA LIOHO |  | Audit Konsultan IATF |  |  |  | 2 | [17 empty] | 2
3 | Gateway Container Line |  | IQA IHT |  |  |  | 2 | [17 empty] | 2
4 | PT TD Automotive Compressor Ind |  | IQA 14001, IHT |  |  |  | 2 | [17 empty] | 2
5 | KFD-supporting for ISO 37001 |  | Training Briberry Risk Assessment |  |  |  | 1 | 1 | [16 empty] | 1 | 1
6 | PT BOLTZ Indonesia |  | Risk Management in IATF 16949, awareness |  |  |  | 2 | 2 | [16 empty] | 2 | 2
7 | Shuang Ying Automotive |  | Core Tools |  |  |  | 2 | [17 empty] | 1 |  | 1
8 | Yang Feng |  | Core Tools |  |  |  | 3 | [17 empty] | 1 |  | 2
9 | NPR, Pasuruan |  | Energy Convertion |  |  |  | 1 | [19 empty] | 1
10 | Indonesia THAI SUMMIT Auto |  | Aligning Control Plan, FMEA & others Core Tools |  |  |  | 2 | [19 empty] | 2
10
11
12
13
14
15
16
17
18
19
20
21
[6 empty] | TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 4 | 6 | 0 | 0 | 0 | 0 | 0
C. Non Chargable : Buat Report di Kantor, Ikut Persentasi Sales, Meeting di Kantor, Program Kerja Perusahaan, Ikut Training
No | Activity |  |  | Client |  |  | All Mandays |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | Remark | Need Help
[7 empty] | Plan | Actual | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | Membuat Materi Training |  |  | Warehouse Management, Tuffindo | [20 empty] | 2 | 1
2 | Ikut Sales Presentasi |  |  | VTRK, | [20 empty] | 2 | 2
|  |  |  | Summit Seoyon | [20 empty] | 1 | 1
|  |  |  | T Hyundai Motor Manufct.Indonesia | [20 empty] | 2 | 1
3 | Meeting di kantor
4 | WFH
[6 empty] | TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0
D. GRAFIK LOADING dan PERFORMANCE KONSULTAN :
|  |  |  | BULAN |  |  |  |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01
|  |  |  | Mandays Planning |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 31 |  | 18 |  | 10 |  | 10
|  |  |  | Mandays Standard (Hari Kerja Sebulan) |  |  |  |  | 21 |  | 18 |  | 22 |  | 19 |  | 15 |  | 21 |  | 21 |  | 22 |  | 22 |  | 22 |  | 22 |  | 22
|  |  |  | % Plan vs Standard |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 140.9% |  | 81.82% |  | 45.45% |  | 45.45%
|  |  |  | Mandyas Actual |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 16 |  | 0 |  | 0 |  | 0
|  |  |  | % Actual vs Plan |  |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | 51.61% |  | 0% |  | 0% |  | 0%
|  |  |  | Chargable Mandays |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 11 |  | 0 |  | 0 |  | 0
|  |  |  | % Chargable vs Standard |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 50% |  | 0% |  | 0% |  | 0%
|  |  |  | Target % Chargable vs Standard |  |  |  |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85%