## Cahyadi
Progress Report Client and Loading
Konsultan |  | : Cahyadi
Tgl Update |  | : 1 Sept 2022
A. Progress Client
No | Client |  | Project |  | Progress |  | Mandays |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | Total Plan | Problem | Action Plan | PIC | Dudate
[5 empty] | Plan | Aktual | Kontrak | Terpakai | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | PT Cikarang Listrindo Babelan |  | ISO 14001:2015 | ISO 14001:2015 | 60% | 42.11% | 19 | 8 |  |  | 1 | 1 | 3 | 1 | 3 | 1 | 1 | 1 |  |  | 2 | 1 | 3 | 3 | 3 |  | 3 |  | 3 |  | 2 |  | 24
2 | PT Cikarang Listrindo Babelan |  | SMK3 | SMK3 | 60% | 50% | 26 | 13 |  |  | 1 | 1 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 4 | 3 | 3 |  | 3 |  | 3 |  | 2 |  | 27
3 | PT Cikarang Listrindo Babelan |  | ISO 45001 (sisa 3 mandays) | SMK3 | 100% | 100% | 3 | 3 | 2 |  | 3 |  |  |  | 2 | 2 | [16 empty] | 7
4 | PT Semen Indonesia (SIG) |  | Sisa mandays - Mapping PROPER Tahun 2021 dan Penyusunan Pedoman Monitoring PROPER | SMK3 | 100% | 100% | 21 | 21 | 12 | 8 | 4 | 3 | 4 | 4 | 6 | 6 | [16 empty] | 26
5 | PT Semen Indonesia (Pabrik Tuban) |  | Penyusunan Pedoman Penyusunan Persetujuan Teknis (Air Limbah, Emisi dan Limbah B3) | SMK3 | 100% | 100% | 5 | 5 |  |  |  |  | 2 | 3 | 1 | 1 | 1 | 1 | [14 empty] | 4
6 | PT Semen Indonesia (SIG) |  | Audiensi Hearing Enviro Regulation KLHK | SMK3, ISO 14001 dan OHSAS 18001 | 50% | 40% | 5 | 2 |  |  | 2 | 1 | 2 | [7 empty] | 1 | 1 |  |  | 1 |  |  |  | 1 |  |  |  | 7
7 | PT Semen Indonesia (SIG) |  | Pra-Assessement PROPER Biru dan Hijau | SMK3, ISO 14001 dan OHSAS 18001 | 100% | 47.17% | 53 | 25 | [10 empty] | 14 | 14 | 8 | 8 | 10 | 3 | 8 |  | 4 |  | 3 |  |  |  | 47
8 | INKALI |  | RKL RPL Rinci & PERTEK | SMK3, ISO 14001 dan OHSAS 18001 | 100% | 66.67% | 15 | 10 |  |  |  |  | 1 |  | 1 | 1 | 2 | 2 | [14 empty] | 4
9 | PT Advics |  | RKL RPL Rinci & PERTEK | SMK3, ISO 14001 dan OHSAS 18001 | 100% | 66.67% | 15 | 10 |  |  | 1 | 1 | 2 | 2 | 1 | 1 | [16 empty] | 4
10 | PT IWWI Tangerang |  | PERTEK IWWI | SMK3, ISO 14001 dan OHSAS 18001 | 100% | 30% | 20 | 6 |  |  |  |  | 3 | 3 |  |  |  |  | 1 | 1 | [12 empty] | 4
11 | PT Odira Energy Karang Agung |  | Input SIMPEL & Development Pengelolaan Lingkungan | SMK3, ISO 14001 dan OHSAS 18001 | 50% | 50% | 20 | 10 |  |  |  |  | 1 | 1 |  |  | 4 | 4 | [10 empty] | 2 |  | 2 |  | 9
12 | PT Odira Energy Karang Agung |  | UKL UPL Site Ridho & Bentayan | SMK3, ISO 14001 dan OHSAS 18001 | 75% | 11.11% | 90 | 10 | [14 empty] | 2 | 2 | 2 |  | 4 |  | 4 |  | 3 |  | 15
13 | PT Waskita Karya Realty |  | Audit Integrasi SMK3LMAP & Persiapan Audit Surveilance | SMK3, ISO 14001 dan OHSAS 18001 | 30% | 19.05% | 21 | 4 | [12 empty] | 1 | 1 | 4 | 3 | 4 |  | 4 |  | 3 |  | 3 |  | 19
14 | PT Kimia Farma Diagnostika |  | ISO 37001:2016 | SMK3, ISO 14001 dan OHSAS 18001 | 25% | 25% | 20 | 5 | [14 empty] | 1 | 5 | 4 |  | 5 |  | 3 |  | 3 |  | 16
[5 empty] | T O T A L | MD All Client |  |  | 14 | 8 | 12 | 7 | 21 | 16 | 17 | 14 | 9 | 9 | 17 | 18 | 14 | 12 | 24 | 19 | 25 | 0 | 23 | 0 | 22 | 0 | 15 | 0
[6 empty] | MD Konsultan Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 3 | 3 | 4 | 4 | 3 | 3 | 0 | 2 | 0 | 0
[6 empty] | MD Konsultan Owner |  |  | 14 | 8 | 12 | 7 | 21 | 16 | 17 | 14 | 9 | 9 | 15 | 16 | 14 | 12 | 21 | 16 | 21 | -4 | 20 | -3 | 22 | -2 | 15 | 0
B. Chargable : Team Project / IHT / Audit Konsultan
No | Client |  | Activity |  | Progress |  | All Mandays |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | Total Plan | Remark | Need Help | Need Help | Need Help
[7 empty] | Plan | Actual | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | PT Softex Sidorajo |  | Audit ISO 14001, 45001 dan SMK3 |  | 100% |  | 3 | 3 |  |  | 3 | 3 | [20 empty] | 3
2 | PT Kimia Farma Tbk. |  | Audit ISO 37001 |  | 100% |  | 5 | 4 | [10 empty] | 1 | 1 | 3 | 3 | [10 empty] | 4
3 | PT Stanley |  | Bonus Project Updating Regulasi |  | 100% |  | 2 | 2 | 2 | 2 | [22 empty] | 2
4 | PT Asahi Denso |  | Sisa mandays ISO 45001 |  | 100% |  | 1 | 1 | 1 | 1 | [22 empty] | 1
5 | Public Training |  | PubliC Training SIMEPL |  | 100% |  | 2 | 2 | 2 | 2 | [22 empty] | 2
6 | PT Yachiyo |  | Audit ISO 45001 |  | 100% |  | 1 | 1 | [6 empty] | 1 | 1 | [16 empty] | 1
7 | PT Djabesmen |  | Audit ISO 14001 |  | 100% |  | 1 | 1 | [6 empty] | 1 | 1 | [16 empty] | 1
8 | PT Semen Gresik Pabrik Rembang |  | IHT Integrasi ISO |  | 100% |  | 8 | 4 | [10 empty] | 4 | 4 | [12 empty] | 4
[6 empty] | TOTAL |  |  | 5 | 5 | 3 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Non Chargable : Buat Report di Kantor, Ikut Persentasi Sales, Meeting di Kantor, Program Kerja Perusahaan, Ikut Training
No | Activity |  |  | Client |  |  | All Mandays |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | Total Plan | Remark | Need Help | Need Help | Need Help
[7 empty] | Plan | Actual | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act | Plan | Act
1 | Management Review |  |  | Kantor SS |  |  | 12 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 12
2 | Arkademy |  |  | Rekaman Materi Arkademi ISO 37001 |  |  | 1 | 1 | 1 | 1 | [22 empty] | 1
3 | Webinar |  |  | PROPER |  |  | 1 | 1 | [6 empty] | 1 | 1 | [16 empty] | 1
4 | Office |  |  | Develop materi & Proposal Project Baru |  |  | 1 | 10 | 0 | 1 |  |  |  | 2 |  | 3 | [5 empty] | 1 |  | 3 | [8 empty] | 0
5 | Ikut Sales Presentasi |  |  | Ikut Sales Presentasi |  |  | 1 | 1 | [8 empty] | 2 | 1 | [14 empty] | 2
6 | WFH (Work From Home) |  |  | Develop materi & Proposal Project Baru |  |  | 0 | 16 | 0 | 3 | 2 | 8 |  | 2 |  | 1 |  | 2 | [14 empty] | 2
[6 empty] | TOTAL |  |  | 2 | 5 | 3 | 8 | 1 | 4 | 2 | 5 | 3 | 3 | 1 | 0 | 1 | 1 | 1 | 3 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
D. GRAFIK LOADING dan PERFORMANCE KONSULTAN :
|  |  |  | BULAN |  |  |  |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 | [6 empty] | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
|  |  |  | Mandays Planning |  |  |  |  | 21 |  | 18 |  | 22 |  | 21 |  | 12 |  | 21 |  | 18 |  | 22 |  | 22 |  | 21 |  | 23 |  | 16
|  |  |  | Mandays Standard (Hari Kerja Sebulan) |  |  |  |  | 21 |  | 18 |  | 22 |  | 21 |  | 15 |  | 21 |  | 21 |  | 22 |  | 22 |  | 21 |  | 22 |  | 22
|  |  |  | % Plan vs Standard |  |  |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 80% |  | 100% |  | 85.71% |  | 100% |  | 100% |  | 100% |  | 104.5% |  | 72.73% | [6 empty] | 21 | 23 | 21 | 21
|  |  |  | Mandyas Actual |  |  |  |  | 18 |  | 18 |  | 20 |  | 21 |  | 12 |  | 21 |  | 16 |  | 19 |  | -4 |  | -3 |  | -2 |  | 0
|  |  |  | % Actual vs Plan |  |  |  |  | 85.71% |  | 100% |  | 90.91% |  | 100% |  | 100% |  | 100% |  | 88.89% |  | 86.36% |  | -18.18% |  | -14.29% |  | -8.696% |  | 0%
|  |  |  | Chargable Mandays |  |  |  |  | 13 |  | 10 |  | 16 |  | 16 |  | 9 |  | 21 |  | 15 |  | 16 |  | -4 |  | -3 |  | -2 |  | 0
|  |  |  | % Chargable vs Standard |  |  |  |  | 61.9% |  | 55.56% |  | 72.73% |  | 76.19% |  | 60% |  | 100% |  | 71.43% |  | 72.73% |  | -18.18% |  | -14.29% |  | -9.091% |  | 0%
|  |  |  | Target % Chargable vs Standard |  |  |  |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85% |  | 85%